## Sheet1
Weeks Tasks | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24
Algorithms Study | bar: Week 1 to Week 4
Draft Algorithms Study Report | bar: Week 3 to Week 4
Complete Study of Algorithms | bar: Week 5 to Week 6
Finalise Stufy of Algorithms | bar: Week 6 to Week 8
Develop Compression Framework | bar: Week 9 to Week 10
Pause Project Work for Break | bar: Week 11 to Week 12
Collect Image Dataset | bar: Week 13
Test Framework | bar: Week 14 to Week 16
Conduct Comparative Analysis | bar: Week 15 to Week 18
Document Findings | bar: Week 16 to Week 19
Debugging & Mitigation | bar: Week 19
Finalise Comparative Analysis | bar: Week 19 to Week 20
Draft Final Report | bar: Week 21 to Week 23
Proofread & Submit | bar: Week 24